## Sprint
|  |  |  | Week #1 | [6 empty] | Week #2 | [6 empty] | Week #3 | [6 empty] | Week #4 | [6 empty] | Week #5 | [6 empty] | Week #6 | [6 empty] | Week #7 | [6 empty] | Week #8 | [6 empty] | Week #9 | [6 empty] | Week #10 | [6 empty] | Week #11
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 97) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37 | D38 | D39 | D40 | D41 | D42 | D43 | D44 | D45 | D46 | D47 | D48 | D49 | D50 | D51 | D52 | D53 | D54 | D55 | D56 | D57 | D58 | D59 | D60 | D61 | D62 | D63 | D64 | D65 | D66 | D67 | D68 | D69 | D70 | D71
 | time axis 2020-02-25 to 2020-05-05
|  |  |  | 210 | 207 | 204 | 201 | 198 | 195 | 192 | 189 | 186 | 183 | 180 | 177 | 174 | 171 | 168 | 165 | 162 | 159 | 156 | 153 | 150 | 147 | 144 | 141 | 138 | 135 | 132 | 129 | 126 | 123 | 120 | 117 | 114 | 111 | 108 | 105 | 102 | 99 | 96 | 93 | 90 | 87 | 84 | 81 | 78 | 75 | 72 | 69 | 66 | 63 | 60 | 57 | 54 | 51 | 48 | 45 | 42 | 39 | 36 | 33 | 30 | 27 | 24 | 21 | 18 | 15 | 12 | 9 | 6 | 3 | 0 | Ideal Burndown
|  |  | 210 | 210 | 207 | 204 | 201 | 198 | 195 | 192 | 189 | 186 | 183 | 180 | 177 | 174 | 171 | 168 | 165 | 162 | 159 | 156 | 153 | 150 | 147 | 144 | 141 | 138 | 135 | 132 | 129 | 126 | 123 | 120 | 117 | 114 | 111 | 108 | 108 | 108 | 108 | 108 | 108 | 106 | 104 | 98 | 92 | 88 | 84 | 80 | 78 | 73 | 70 | 67 | 60 | 55 | 50 | 48 | 45 | 42 | 39 | 35 | 30 | 24 | 18 | 13 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | Remaining Hrs (Total)
Enable all users to place book in shopping cart | Requirements Gathering | All team members | 3 | 2020-02-25: 3
| Writing User Story | Manasa | 4 | 2020-02-26: 3; 2020-02-27: 1
System Design | Architecture Diagram | Sneha | 2 | 2020-02-27: 2
|  | Manasa | 2 | 2020-02-28: 2
| Deciding Technology Stack | All team members | 2 | bar: 2020-02-25 to 2020-04-30; 2020-05-05
System Setup | Setting up server | Ambika | 2 | 2020-02-29: 2; 2020-03-01: 1
| Setting up frontend | Ambika | 3 | 2020-03-01: 3
| Researching on AWS resources | All team members | 4 | 2020-03-02: 3
Login API | Front End Login Development | Ambika | 6 | 2020-03-03: 3; 2020-03-04: 3
| Design - User Module | Sneha | 6 | 2020-03-05: 3; 2020-03-06: 3
| Design - Admin Module | Manasa | 4 | 2020-03-07: 3; 2020-03-08: 1
System Design - 2 | DB Modeling - Discussion | All team members | 1 | bar: 2020-03-08
| DB Tables design - class diagram | Manasa | 5 | 2020-03-08: 1; 2020-03-09: 3; 2020-03-10: 2
| DB Setup | Sneha | 6 | 2020-03-10: 1; 2020-03-11: 3; 2020-03-12: 2
| Front End Design Discussion | All team members | 1 | bar: 2020-03-12
API Development & Feedback (Agile) | Design User Registration functionality with validations | Ambika | 10 | 2020-03-13: 3; 2020-03-14: 3; 2020-03-15: 3; 2020-03-16: 1
| Add routers , tabs and navigation pages | Ambika | 6 | 2020-03-16: 2; 2020-03-17: 3; 2020-03-18: 1
| Search and Browse rental location and vehicles functionality | Sneha | 10 | 2020-03-18: 2; 2020-03-19: 3; 2020-03-20: 3; 2020-03-21: 2
| Admin API to add vehicles | Manasa | 3 | 2020-03-23: 2; 2020-03-24: 1
| Backend Implementation for Search and Browse functionality. | Sneha | 5 | 2020-03-24: 2; 2020-03-25: 3
| UI design for Vehicle reservation. | Sneha | 5 | 2020-03-26: 3; 2020-03-27: 2
| Complete the Vehicle reservation functionality | Sneha | 8 | 2020-03-27: 1; 2020-03-28: 3; 2020-03-29: 3; 2020-03-30: 2
| React and Node application deployment on AWS EC2. | Sneha | 5 | bar: 2020-03-30
| Attaching Load balancer wih auto scaling groups to EC2. | Sneha | 5 | 2020-04-04: 2; 2020-04-05: 2; 2020-04-06: 3
| User Registration | Ambika | 8 | 2020-04-06: 3; 2020-04-07: 5
| User Login | Ambika | 8 | 2020-04-07: 1; 2020-04-08: 4; 2020-04-09: 3
| Search and Browse rental location and vehicles | Sneha | 5 | 2020-04-09: 1; 2020-04-10: 4
| My reservation tab with option to Return | Manasa | 6 | 2020-04-11: 2; 2020-04-12: 4
| Admin API to terminate memberships | Manasa | 5 | 2020-04-12: 1; 2020-04-13: 3; 2020-04-14: 2
| Dynamic Pricing API on reservations | Manasa | 10 | 2020-04-14: 1; 2020-04-15: 3; 2020-04-16: 3; 2020-04-17: 3
| User billing API for cancellation and returning vehicles | Manasa | 5 | 2020-04-18: 3; 2020-04-19: 2
| Vehicle reservation and validation | Sneha | 5 | 2020-04-19: 1; 2020-04-20: 3; 2020-04-21: 1
| Condition and Comment for returned vehicle | Manasa | 3 | 2020-04-21: 2; 2020-04-22: 1
| My membership tab with option to extend membership | Ambika | 4
| My membership tab with option to terminate | Ambika | 4 | 2020-04-22: 2; 2020-04-23: 3; 2020-04-24: 2
| For Admin, terminate user membership - update | Manasa | 4 | 2020-04-24: 1; 2020-04-25: 3
| Add and update database using queries for individual vehicles and rental locations. | Manasa | 3 | 2020-04-26: 3
| Password encryption + validation | Ambika | 6 | 2020-04-27: 3
| User authorization | Ambika | 3 | 2020-04-28: 2
| User Authentication | Ambika | 3 | 2020-04-28: 3
| Architecture Diagram + Interface diagram | Manasa | 3 | 2020-04-29: 3
| Rest of all DB Queries | Manasa | 3 | 2020-04-29: 3
| Writing github readme | Manasa | 3 | 2020-04-28: 8; 2020-04-29: 3
| AWS with load balancer | Sneha | 8 | 2020-04-30: 2
| 3-Tier architecture-deployment diagram | Manasa | 2
| Login for user and admin with backened and bug fixes | Ambika | 8 | 2020-04-26: 8
Team:
Manasa Hari | 7 hours / Week
Ambika Na | 7 hours / Week
Sneha Patil | 7 hours / Week
Total Available Hours During Sprint: | 21*10=210